## Index
S.No | Main Menu | Sub Menu | Defect Category |  |  | Total | Defect Status |  |  |  |  | Suggestion Status
|  |  | Functional | UI | Both |  | New | IP | Fixed Not Deployed | Closed | Reopen | New | IP | Fixed Not Deployed | Closed | Reopen
1 | Admin-Master | Company | 1 |  |  | 1 | 1
2 | Admin-Master | Designation Creation |  |  | 2 | 2 | 2
3 | Admin-Master | Division Creation |  |  | 2 | 2 | 2 |  |  |  |  | 1
4 | Admin-Master | Shift Master |  | 1 |  | 1 | 1
5 | Admin-Master | Plant Master |  |  | 1 | 1 | 1
6 | Admin-Master | Product Category |  |  | 1 | 1 | 1
7 | Admin-Master | Product Target Fixation |  |  | 1 | 1 | 1
8 | Admin-Master | Category - Rate Fixation | 1 | 1 |  | 2 | 2
9 | Admin-Master | Product Sequence |  | 1 |  | 1 | 1
10 | Admin-Master | Field Force | 1 |  |  | 1 | 1
11 | DMS-Master | Salesman List |  |  | 1 | 1 | 1
12 | DMS-Master | Product Category List |  | 1 |  | 1 | 2
13 | DMS-Master | Customer List |  | 1 | 1 | 2 | 2
14 | DMS-Order | Purchase Order List |  | 2 | 1 | 3 | 2
15 | DMS-Order | Purchase Invoice List |  | 1 |  | 1 | 1
16 | DMS-Order | Add Channel |  | 1 | 1 | 2 | 2
17 | DMS-Order | Sales Invoice List |  | 1 | 2 | 3 | 3
18 | Mobile App-Login | Login Page | 1 |  |  | 1 | 1
19 | DMS-Master | Salesman List | 1 |  |  | 1 | 1
20 | DMS-Order | Sales Invoice List | 1 |  |  | 1 | 1
21 | DMS-Order | Counter Sales List | 2 |  | 2 | 4 | 4
22 | Admin-Master | Retailer Details List | 2 |  |  | 2 | 2
23 | Admin-Master | New Retailer Approval | 1 | 1 |  | 2 | 2
24 | Admin-Master | Retailer Target Fixation |  |  | 3 | 3 | 3
25 | Admin-Master | Product Target Fixation | 1 |  |  | 1 | 1
26 | Admin-Master | Route Creation |  | 1 | 2 | 3 | 3
27 | Mobile App | My Day Plan |  |  | 1 | 1 | 1
28 | Mobile App | Add TP Entry |  | 1 |  | 1 | 1
29 | Mobile App | Tour Plan Details |  | 1 |  | 1 | 1
30 | Mobile App | Closing Stock Entry |  | 1 |  | 1 | 1
31 | Mobile App | Add New retailer |  |  | 1 | 1 | 1
32 | Mobile App | Secondary Order | 1 |  |  | 1 | 1
33 | Mobile App | Collection Details |  |  | 1 | 1 | 1
|  | Total | 13 | 15 | 23 | 51 | 51
[7 empty] | Total Issues | Blocker | Major | Minor | Total
[7 empty] | 51 | 5 | 31 | 15 | 51

## Admin
S.No | Main Menu | Sub Menu | Type of Defect | Category | Description | Steps To Reproduce / Actual and Expected | Defect Screenshot Link | Status | priority | Severity | Assignee | Raised Date | Fixed Date | Dev Comments | QA Comments
1 | Master | Company | Defect | Functional | On clicking Company name,Alias Name,City->It's displayed the Server Error in '/' Application. Incorrect syntax near ')'. | 1.Launch the application 2.Enter the Valid Admin Credentials /(User Name: adminhapll/password: hapll) 3.Click the Master Menu 4.Click the Company Menu 5.Click the grid header company name Actual Result: It's displayed the Server Error in '/' Application.Incorrect syntax near ')'. Expected Result: Company Name Page should be displayed. | https://drive.google.com/open?id=1HAGsTO8Hktg_MKICllm6Sy8cjtEnRWgc | New | High | Major |  | 2020-04-27
2 | Master | Designation Creation | Defect | Both | Once the Designation Created successfully the data should be clear. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the DesignationCreation Menu 5.Click the Add Button 6.Enter the Short Name,Designation,Type,Division Name,BackColor 7.Hit the Save Button Actual Result: Saved data displayed in the page. Expected Result: Data should be clear. | https://drive.google.com/file/d/1CZw9PQ3jfaz9uEuXUTScP3_hXOsY-JHE/view?usp=sharing | New | Medium | Minor |  | 2020-04-27
3 | Master | Designation Creation | Defect | Both | The download the excel sheet header name with hyperlink. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the DesignationCreation Menu 5.Click the download the excel icon Actual Result: Excel sheet have a hyperlink header Expected Result: No need to display the header in Excel sheet | https://drive.google.com/open?id=1PjV5wejXguPDV6j1Uj24VagreNLxbbQs | New | Medium | Major |  | 2020-04-27
4 | Master | DivisionCreation | Defect | Both | Edit the Division Created data the success message does not displayed in the page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Division Creation Menu 5.Click the Edit Button 6.Enter the Division Code,Division Name 7.Hit the Save Button Actual Result: Edit Successfully message missing Expected Result: Successfully message should be displayed in the updated the data. | https://drive.google.com/open?id=1UHAxV8qI3uwxu5v1y3QETt39NxjCSrSx | New | Medium | Major |  | 2020-04-27
5 | Master | DivisionCreation | Defect | UI | DivisionCreation -> Edit the Division page -> Click the back button it's should be navigate to the division view grid page. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Division Creation Menu 5.Click the Edit Button 6.Enter the Division Code,Division Name 7.Hit the Back Button Actual Result: Edit - >Back Button navigate to edit page itself. Expected Result: On clicking Back button Navigates to Grid view page. | https://drive.google.com/open?id=1cgC0ur6XB-ZXTFi3yvDhhvXCJVPue4jc | New | Low | Minor |  | 2020-04-27
6 | Master | DivisionCreation | Suggestion | Both | DivisionCreation -> Reactivation button missing in the Division creation page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Division Creation Menu Actual Result: Reactivation button missing in the Division creation page Expected Result: Add the Reactivation button in the Division creation page | https://drive.google.com/open?id=1Aopx_Bg8HlUXlnKd5wqaILDm0Xr38kxQ | New | Medium | Major |  | 2020-04-27
7 | Master | Shift Master | Defect | UI | Shift Master -> Pagination First Button icon missing. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Shift Master Menu 5.Check the pagination icon missing Actual Result: Pagination First Button icon missing. Expected Result: Add the Pagination First Button icon . | https://drive.google.com/open?id=1awJ-AIIVIQ2WS9uzmJes8TkVKXv7HbXN | New | Low | Minor |  | 2020-04-27
8 | Master | Plant Master | Defect | Both | Plant Master -> Pin code accept the alphanumeric values. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Plant Master Menu 5.Enter the Pin Code Actual Result: Pin code accept the alphanumeric values. Expected Result: Pin code not accept the alphanumeric values. | https://drive.google.com/open?id=1wVOOin8r4Asz1pORh3PAQ81dNM8mAZuc | New | Medium | Major |  | 2020-04-27
9 | Master | Product Category | Defect | Both | Product Category- Need to set back button in the Product Category Page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Product Category Menu Actual Result: 'Back' Button is missing. Expected Result: 'Back' Button should be added. It's should lead to previous page. | https://drive.google.com/open?id=1WzbNhLl8Ss4hQy4GHaJNPqJjYCdn3YcU | New | Medium | Major |  | 2020-04-28
10 | Master | Product Target Fixation | Defect | Both | Product Target Fixation Click save button -> It's displayed the error message No row enter the values | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Product Target Fixation Menu Actual Result: Error message , 'No row enter the values' . Expected Result: Product Target Fixation Details should be saved without any error message. | https://drive.google.com/open?id=13cXw2OI8NnyAI1aNvVpXGt4oMeldhJZO | New | High | Major |  | 2020-04-28
11 | Master | Category - Rate Fixation | Defect | Functional | Category - Rate Fixation - Category Name does not displayed in the Category Add Page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Category - Rate Fixation Menu Actual Result: Category Name list not displayed in the 'Category Add' Page. Expected Result: Category Name list should be displayed in the 'Category Add' Page . | https://drive.google.com/open?id=19GqVcf0SDT7_fkwhLIPDH2Y3mKTrODqE | New | High | Blocker |  | 2020-04-28
12 | Master | Category - Rate Fixation | Defect | UI | Category - Rate Fixation - Category Name Header Title missing | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Category - Rate Fixation Menu Actual Result: 'Category Name' Header 'Title' missing Expected Result:'Category Name' title should be displayed. | https://drive.google.com/open?id=1g1bQxBRqy8KoF0PW_kVsMMhZq3ylVJr7 | New | Medium | Minor |  | 2020-04-28
13 | Master | Product Sequence | Defect | UI | View the Product Sequence List -> Windows Pop Message spelling mistake. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Product Sequence Menu Actual Result: Success message spelling is displayed as 'Sccuss' Expected Result: Success message spelling should be displayed 'Success' | https://drive.google.com/open?id=1MwRK00byT0TJurGf6sDLOXBVGoHhelOe | New | Medium | Minor |  | 2020-04-28
14 | Master | Field Force | Defect | Functional | Field Force Page have a two submit button. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Field Force Menu Actual Result: Field Force Page have a two submit button. on scrolling the one of the 'Submit' button. Expected Result: One submit button enough to this page | https://drive.google.com/open?id=1th8RxN_hi70MRX9wmZLSxU7bcHMEwJIS | New | High | Major |  | 2020-04-28
15 | Master | Retailer Details List | Defect | Functional | 'Purchase Slab' Name is not displayed in the Retailer Details List Page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the 'Master' Menu 4.Click the 'Retailer Details List' Menu. 5.Click the 'Purchase Slab' Name dropdown. Actual Result: 'Purchase Slab' Name list not displayed in the 'Retailer Details List' Page. Expected Result: 'Purchase Slab' Name list should be displayed in the 'Retailer Details List ' Page ." | https://drive.google.com/open?id=1bpLamYBXPQ1LHC6y1NS9YXtNgKAwcvFc | New | High | Major |  | 2020-05-05
16 | Master | Retailer Details List | Defect | Functional | On clicking the Retailer Details List 'View' Button is not displayed the Created Retailer Details in the Page. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the 'Retailer Details List' Menu 5.Click the View Button Actual Result: On clicking the Retailer Details List 'View' Button is not displayed the Created Retailer Detail in the Page. Expected Result: On clicking the Retailer Details List 'View' Button the Retailer Details should be displayed in the Page. | https://drive.google.com/open?id=1u_o20IvIXaszMGGxL3nFjtrkITFa4ZGy | New | High | Major |  | 2020-05-05
17 | Master | New Retailer Approval | Defect | Functional | On clicking the New Retailer Approval 'View' Button is not displayed the Created Retailer Approval Details in the Page. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the 'New Retailer Approval' Menu 5.Click the View Button Actual Result: On clicking the New Retailer Approval 'View' Button is not displayed the Created Retailer Approval Details in the Page. Expected Result: On clicking the New Retailer Approval 'View' Button the Retailer Approval Details should be displayed in the Page. | https://drive.google.com/open?id=10JLKniRLMseehJc9V4PHVO-Neb9raz4M | New | High | Major |  | 2020-05-05
18 | Master | New Retailer Approval | Defect | UI | View the New Retailer Approval List -> Windows Pop Message spelling mistake. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the New Retailer Approval Menu Actual Result: Success message spelling is displayed as 'Sccuss' Expected Result: Success message spelling should be displayed 'Success' | https://drive.google.com/open?id=1NazUEYsb9stv708dS904eBtEcYegk805 | New | Medium | Minor |  | 2020-05-05
19 | Master | Retailer Target Fixation | Defect | Both | Once the New Retailer Created successfully the data should be cleared. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the New Retailer Menu 5.Click the Add Button 6.Enter the Retailer Name, Retailer Designation,Retailer Type. 7.Hit the Save Button Actual Result: Once the New Retailer Created successfully the data displayed in the 'Retailer Creation' Page. Expected Result: Once the New Retailer Created successfully the data should be cleared in the 'Retailer Creation' Page. | https://drive.google.com/open?id=1Nkh5sGBh2A_iycb73OUdRRB44_GVodd4 | New | High | Major |  | 2020-05-05
20 | Master | Retailer Target Fixation | Defect | Both | On clicking the Retailer Target Fixation 'Save' Button and the data saved two times with duplicate data . | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the 'Product Target Fixation' Menu 5.Enter the Product Target Fixation data. 6.Click the 'Save' Button Actual Result: On clicking (once) the Product Target Fixation 'Save' Button the Product Target Fixation data saved two times with duplicate data . Expected Result: On clicking (once) the Product Target Fixation 'Save' Button the Product Target Fixation data saved one times without duplicate data . | https://drive.google.com/open?id=1lN0tMV3g0dD1qWlvp1aAAoo7k2Kdk4yi | New | High | Major |  | 2020-05-05
21 | Master | Retailer Target Fixation | Defect | Both | On clicking Retailer Target Fixation View Button->It's displayed the Server Error in '/' Application. Internal server error')'. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the 'Retailer Target Fixation' Menu 5.Click the View Button Actual Result: It's displayed the Server Error in '/' Application.Internal Server Error ')'. Expected Result: Retailer Target Fixation List should be displayed. | https://drive.google.com/open?id=1mxRo0MPpxCie1bKcYwp21HT-uxpKdy6b | New | High | Major |  | 2020-05-05
22 | Master | Product Target Fixation | Defect | Functional | 'Product Target Fixation'->remove the unwanted total values displayed in the Product Target Fixation List Page. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the 'Product Target Fixation' Menu 5.Click the View icon of 'Product Target Fixation' Actual Result: Unwanted total values are displayed in the 'Total' textfield. Expected Result: Unwanted total values should be cleared in the 'Total' textfield. | https://drive.google.com/open?id=1SPo7nNopqb_IgjQpPp4F5p-OCmkNxT2m | New | High | Major |  | 2020-05-05
23 | Master | Route Creation | Defect | Both | Once the Route Created successfully the data should be cleared. | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Route Creation Menu 5.Click the Add Button 6.Enter the Route Creation Name, Route Creation Designation,Route Creation Type,Route Division Name 7.Hit the Save Button Actual Result: Created Data displayed in the Route Creation Page. Expected Result: Created Data should be cleared in the 'Route Creation' Page. | https://drive.google.com/open?id=1HxcFboiSYjUH7Zx_8Rz0EzQSnGWjcrLm | New | High | Major |  | 2020-05-05
24 | Master | Route Creation | Defect | Both | Edit the 'Route' Created data the success message is not displayed in the page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Route Creation Menu 5.Click the Edit Button 6.Enter the Route Code,Route Name 7.Hit the Save Button Actual Result: Edited Successfully message missing in the Route Creation Page. Expected Result: Edited Successfully message should be displayed in the Route Creation Page. | https://drive.google.com/open?id=1gzV-dojwJ7V_LxzgmJK5T7vKQYoc-ytA | New | High | Major |  | 2020-05-05
25 | Master | Route Creation | Defect | UI | Route Creation -> 'Save' and 'Cancel' Button alignment missing in the 'Route Creation' page | 1.Launch the application 2.Enter the Valid Admin Credentials / (User Name: adminhapll / password: hapll) 3.Click the Master Menu 4.Click the Route Creation Menu 5.View the 'Save' Button Actual Result: Unwanted spaces are displayed in the 'Save' and 'Cancel' Button. Expected Result: Unwanted spaces should be trimmed in the 'Save' and 'Cancel ' Button. | https://drive.google.com/open?id=1IstLUcaiZYYcgQcJay1Hz0-1iIquFfoU | New | High | Minor |  | 2020-05-05

## DMS
S.No | Main Menu | Sub Menu | Type of Defect | Category | Description | Steps To Reproduce / Actual and Expected | Defect Screenshot Link | Status | priority | Severity | Assignee | Raised Date | Fixed Date | Dev Comments | QA Comments
1 | Master | Salesman List | Defect | Both | 'Add New' Salesman Button not able to click the button. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Master Menu 4.Click the Salesman List Menu 5.Click the Add New Salesman Button Actual Result: 'Add New' Salesman button is not clickable. Expected Result: 'Add New' Salesman Button should be clickable the button and lead to add new sales man page. | https://drive.google.com/open?id=1bvyku8u7V9js0aK652bZUAF6D67XO2Zd | New | High | Blocker |  | 2020-04-29
2 | Master | Product Category List | Defect | UI | Product Category List-> Pagination First Button icon missing. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Master Menu 4.Click the Product Category List Menu 5.Check the pagination icon missing Actual Result: Pagination 'First' Button icon is not displayed in the 'Product Category List' page. Expected Result: Pagination 'First' Button icon should be displayed in the 'Product Category List' page. | https://drive.google.com/open?id=1VpI7otTnAzyxhfBQR1wkDpiJ4IEFozpz | New | Low | Minor |  | 2020-04-29
3 | Master | Customer List | Defect | Both | Customer List -> User is able to Create a Customer with blank Category Code and Category Name. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Master Menu 4.Click the Customer List Menu 5.Click the Add New Customer List Button Actual Result: Logged-in User is able to Create a Customer with blank 'Category Code' and 'Category Name'. Expected Result: Logged-in User should not allowed to create a customer with blank 'Category Code' and 'Category Name'. | https://drive.google.com/open?id=1WvFe2OjfAYTW3A3DdRq55RXDL2YgorbH | New | High | Blocker |  | 2020-04-29
4 | Master | Customer List | Defect | UI | Customer List -> Once Customer Created successfully and User Click the 'Ok' button it's navigates to 'Channel' Grid page. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Master Menu 4.Click the Customer List Menu 5.Click the Add New Customer List Button Actual Result: Customer Created successfully and On Clicking 'Ok' button it wrongly navigates to 'Channel' Grid page. Expected Result: After successful customer creation , On Clicking the 'Ok' button it should be navigates to 'Customer' Grid page. | https://drive.google.com/open?id=1xJAG0sEFspjUW2YE3HH4wBdsK6By9h4j | New | High | Major |  | 2020-04-29
5 | Order | Purchase Order List | Defect | UI | Purchase Order List -> Add New Purchase Order -> Total : alignment missing in the 'Purchase Order List' page | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the Purchase Order List Menu 5.Click the 'Add New' Purchase Order Actual Result: Unwanted spaces are displayed in the 'Total' Label. Expected Result: Unwanted spaces should be trimmed in the 'Total' Label. | https://drive.google.com/open?id=17IAzNvfnA3Xmd-mr3Vgx6cTM7kHC-WL6 | New | Low | Minor |  | 2020-04-29
6 | Order | Purchase Order List | Defect | UI | Purchase Order List -> Add New Purchase Order -> To : Billing Address title remove the unwanted space in the title | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the Purchase Order List Menu 5.Click the 'Add New' Purchase Order Actual Result: Unwanted spaces are displayed in the 'To : Billing Address' Label. Expected Result: Unwanted spaces should be trimmed in the 'To : Billing Address' Label. | https://drive.google.com/open?id=1WzE6dXcySXjj1gutMXzPn4Y7L1YM5Npq | New | Low | Minor |  | 2020-04-29
7 | Order | Purchase Order List | Defect | Both | Click the View icon of 'Purchase Order List' -> Does not displayed any 'Purchase Order List' details. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the Purchase Order List Menu 5.Click the View icon of 'Purchase Order List' Actual Result: Displayed of 'Purchase Order List' details is not displayed. Expected Result: Displayed of 'Purchase Order List' details is should be displayed. | https://drive.google.com/open?id=1dvInXYSv-P5kVHU_LKm85AW4knmdTRR1 | New | High | Major |  | 2020-04-29
8 | Order | Purchase Invoice List | Defect | UI | Click the View icon of 'Purchase Invoice List' -> Does not displayed any 'Purchase Invoice List' details. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Purchase Invoice List' Menu 5.View the 'Purchase Invoice List' Details Actual Result: On Clicking the view icon 'Purchase Invoice List' details is not displayed. Expected Result: On Clicking the View icon 'Purchase Invoice List' details is should be displayed. | https://drive.google.com/open?id=1kS6zgnPvRMP17OsoyWkAKL4ErW5SgYzi | New | High | Major |  | 2020-04-30
9 | Order | Add Channel | Defect | Both | Add Channel'->Need to set back button in the 'Add Channel Page | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Add Channel' Menu Actual Result: 'Back' Button is missing. Expected Result: 'Back' Button should be added. It's should lead to previous page. | https://drive.google.com/open?id=1CqooL2JnZgxYzgqU1rKXqXCNli3AM5iM | New | Medium | Minor |  | 2020-04-30
10 | Order | Add Channel | Defect | UI | Add Channel '->'Add Channel ' Header Title missing | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the' Add Channel ' Menu Actual Result: 'Add Channel ' Header 'Title' missing Expected Result: 'Add Channel ' title should be displayed. | https://drive.google.com/open?id=13cSWqAbXTsGW99hSz6gOZct6n9wvBVQB | New | High | Major |  | 2020-04-30
11 | Order | Sales Invoice List | Defect | UI | 'Sales Invoice List'->Need to set vertical scrollbar in the 'Sales Invoice List ' Page | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the Sales Invoice List Menu 5.Click the View icon of 'Sales Invoice List' Actual Result: Vertical scrollbar is missing. Expected Result: vertical scrollbar should be added. | https://drive.google.com/open?id=1tCCNnIL_d7u9pIjmuP0fjS-7I90uU4RU | New | High | Major |  | 2020-04-30
12 | Order | Sales Invoice List | Defect | Both | Sales Invoice List'->remove the unwanted total values displayed in the Sales Invoice List Page | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Sales Invoice List ' Menu 5.Click the View icon of 'Sales Invoice List' Actual Result: Unwanted total values are displayed in the 'Total' textfield. Expected Result: Unwanted total values should be cleared in the 'Total' textfield. | https://drive.google.com/open?id=1md1aAQJoHYfL77ZTw7d6YfjNFBBjdSnI | New | High | Major |  | 2020-04-30
13 | Order | Sales Invoice List | Defect | Both | Add Sales Invoice ->Quantity,Discount(%),Free accept the alphanumeric values. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Sales Invoice List ' Menu Actual Result: 'Quantity,Discount(%),Free' accept the alphanumeric values. Expected Result: 'Quantity,Discount(%),Free' not accept the alphanumeric values. | https://drive.google.com/open?id=1mWl7V6Fa50cZhhnKUrTiQu3FPYwKqml5 | New | High | Major |  | 2020-04-30
14 | Master | Salesman List | Defect | Functional | 'Add New' Salesman Button not able to clickable. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Master Menu 4.Click the Salesman List Menu 5.Click the Add New Salesman Button Actual Result: 'Add New' in Salesman button is not clickable. Expected Result: 'Add New' in Salesman Button should be clickable the button and lead to add new sales man page. | https://drive.google.com/open?id=1vw8XcIKSkJD8S0Et7_j4Q4ehjd1RP8lq | New | High | Major |  | 2020-05-04
15 | Order | Sales Invoice List | Defect | Functional | 'Save Counter New' Button not able to clickable. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Sales Invoice List ' Menu Actual Result: 'Save Counter New' in Sales Invoice List button is not clickable. Expected Result: 'Save Counter New' in Sales Invoice List Button should be clickable the button and lead to add Sales Invoice page. | https://drive.google.com/open?id=1kkSLGDlCeyfGFGIn5hJzNT8pbJ0vI_aF | New | High | Blocker |  | 2020-05-04
16 | Order | Counter Sales List | Defect | Functional | On clicking the 'Save Counter New' Button the Counter Sales data saved two times with duplicate data . | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu. 4.Click the 'Sales Invoice List ' Menu. 5.Click the 'Save Counter New' Button. Actual Result: On clicking (once) the 'Save Counter New' Button the Counter Sales data saved two times with duplicate data . Expected Result: On clicking (once) the 'Save Counter New' Button the Counter Sales data saved one times without duplicate data . | https://drive.google.com/open?id=1R2DymLQ1FdCrVvxKZ5NMHSU4HoHqwSJp | New | High | Major |  | 2020-05-04
17 | Order | Counter Sales List | Defect | Both | On clicking Counter Sales List Button->It's displayed the Server Error in '/' Application. Internal server error')'. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Counter Sales List' Menu Actual Result: It's displayed the Server Error in '/' Application.Internal Server Error ')'. Expected Result: Counter Sales List Page should be displayed. | https://drive.google.com/open?id=1fbLXhntfpb6_A2laEL7v6W20iD0INgNm | New | High | Major |  | 2020-05-04
18 | Order | Counter Sales List | Defect | Functional | Counter Sales-> User is able to Create a Counter Sales with blank data. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Sales Invoice List ' Menu 5.Do not enter value any of the fields in the page(Quantity,Free,Percentage) 6.Click the 'Counter sales' button. Actual Result: Logged-in User is able to Create a Counter Sales with blank data. Expected Result: Logged-in User should not allowed to create a Counter Sales with blank data. | https://drive.google.com/open?id=1QEmTw1MzofOgGItKqukMxJGjbeUopRyY | New | High | Major |  | 2020-05-04
19 | Order | Counter Sales List | Defect | Both | Counter Sales List->'Order ID' Number is missing in 'Counter sales list' page. | 1.Launch the application 2.Enter the Valid DMS Credentials /(Username:Test001DSM /password:Test@1234) 3.Click the Order Menu 4.Click the 'Counter Sales List' Menu Actual Result: 'Order ID' Number is missing in 'Counter sales list' page. Expected Result: 'Order ID' Number is should be displayed in the 'Counter Sales List' Page. | https://drive.google.com/open?id=1ZU95U0j3hBcTmqCmEfXjnPqwA1Jntg-7 | New | High | Major |  | 2020-05-04

## Mobile
S.No | Main Menu | Sub Menu | Type of Defect | Category | Description | Steps To Reproduce / Actual and Expected | Defect Screenshot Link | Status | priority | Severity | Assignee | Raised Date | Fixed Date | Dev Comments | QA Comments
1 | Mobile App | Login Page | Defect | Both | Installed successfully But user not able to login this app.It shows Uname and pwd incorrect. | 1.Installed the SAN Sales App 2.Enter the Valid DMS Credentials /(Username:Test001/password:Test1234) 4.Click the 'Login' Button. Actual Result: On Clicking the 'Login' Button, It shows Uname and pwd incorrect.. Expected Result: On clicking 'Login' Button It navigates to San App Home Page. | https://drive.google.com/open?id=15eytMuBPri0uBJpzX3hVFqU3knwMxMMx | New | High | Blocker |  | 2020-04-30
2 | Mobile App | My Day Plan | Defect | Both | Once the 'My Day Plan' Created successfully the data should be cleared in the page. | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the My Day Plan Menu 4.Enter the Work Type,Distributors Name,route name. 5.Hit the Save Button Actual Result: Saved data displayed in the page. Expected Result: Saved data should be cleared in the page. | https://drive.google.com/open?id=1h6Gs0sz_vUYkIfgIM57dfKPhG9FlqXeG | New | Medium | Minor |  | 2020-05-06
3 | Mobile App | Add TP Entry | Defect | UI | View the Add TP Entry -> Calender grid may-month spelling mistake. | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the Add TP Entry Menu 4.View the calender grid Actual Result: Calender Grid Month spelling is displayed as 'MAI' Expected Result: Calender Grid Month spelling should be displayed 'MAY' | https://drive.google.com/open?id=1JIKBE7TMoqa1zwLL7sNobuHhv3evcQEt | New | Medium | Minor |  | 2020-05-06
4 | Mobile App | Tour Plan Details | Defect | UI | Tour Plan Details-> 'Edit' Button alignment missing in the 'Tour Plan Details' page | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the 'Tour Plan Details' Menu 4.View the 'Edit' Button Actual Result: Unwanted spaces are displayed in the 'Edit' Button. Expected Result: Unwanted spaces should be trimmed in the 'Edit' Button. | https://drive.google.com/open?id=1F2cOwuvFpdNCMwA1NUtq6BUBRGFmunSB | New | Medium | Minor |  | 2020-05-06
5 | Mobile App | Closing Stock Entry | Defect | UI | Closing Stack Entry-> 'Distributors Name' Label alignment missing in the 'Closing Stock Entry' page | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the ' Closing Stack Entry ' Menu 4.View the 'Distributors Name' Label Actual Result: Unwanted spaces are displayed in the 'Distributors Name' Label. Expected Result: Unwanted spaces should be trimmed in the 'Distributors Name' Label. | https://drive.google.com/open?id=1f9UnRlhz1D6lsGD0GwVkG09zmrSTyHlN | New | Medium | Minor |  | 2020-05-06
6 | Mobile App | Add New retailer | Defect | Both | Add New retailer-> 'retailer photo' alignment missing in the 'Add New retailer' page | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the 'Add New retailer' Menu 4.View the 'Distributors Name' Label Actual Result: Unwanted spaces are displayed in the 'retailer photo' Expected Result: Unwanted spaces should be trimmed in the 'retailer photo' | https://drive.google.com/open?id=1E6O5aZHqFEK9D5qTnT829SnwRTeT3ntf | New | High | Major |  | 2020-05-06
7 | Mobile App | Secondary Order | Defect | Functional | 'retailer' Name is not displayed in the Secondary Order Page | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the 'Secondary Order' Menu. 4.Click the 'retailer' Name dropdown. Actual Result: 'retailer' Name list not displayed in the 'Secondary Order' Page. Expected Result: 'retailer' Name list should be displayed in the 'Secondary Order ' Page ." | https://drive.google.com/open?id=1BmyLH-fUPSgszM0Nno9jjKicK8ywO_A3 | New | High | Blocker |  | 2020-05-06
8 | Mobile App | Collection Details | Defect | Both | On clicking the 'View' Button -> Collected amount is not displayed in the Collection Details Page. | 1.Launch the app 2.Enter the Valid BDE Credentials / (User Name: HAPLTNBDE1 / password: hap) 3.Click the 'Collection Details' Menu 4.Click the View Button Actual Result: On clicking the 'View' Button->Collected amount is not displayed in the Collection Details Page. Expected Result: On clicking the 'View' Button ->Collected amount should be displayed in the Collection Details Page. | https://drive.google.com/open?id=1CmpYFuriWFrVg-3psiO7flszaFtc0dvJ | New | High | Major |  | 2020-05-06

## Query Log
S.No. | Date | Module Name | Page Name | Question | Raised By | Clarification | Clarified By | Comments
1 | 2020-04-22 | Division | Division | Division code - No.of.digit |  | Closed
2 | 2020-04-22 | Product | Category | Category Code - No.of .digit |  | Closed
3 | 2020-04-22 | Product | Brand Creation | Brand Code-No.of.digit |  | Closed
4 | 2020-04-22 | Product | Product Detail Creation | Conversion factor , ERP Code,Target values |  | Closed
5 | 2020-04-22 | Geography | Area Creation | Area Creation code, |  | Closed
6 | 2020-04-22 | Field Force | Field Force Creation | Why we created Field Force-> Login & Joining Details |  | Closed
7 | 2020-04-22 | Distributor | Distributor Creation | Distributor Code,ERP Code,Norm Value,Cut-Off Time |  | Closed
8 | 2020-04-27 | Distributor | Distributor Creation | When Distributor Creation it's shows the same error message Error Message-> rollback transaction request has no corresponding begin transaction |  | Closed
9 | 2020-04-27 | Retailer | Retailer Detail Creation | Latitude,Longitude , Channel |  | Closed
10 | 2020-04-28 | Geography | Area Creation | Deactivate -> x mark |  | Closed
11 | 2020-04-28 | Product | Category | Deactivate. |  | Closed
12 | 2020-04-28 | APk File | APK File | Installed successfully but i'm not able to login the email id |  | Closed
13 | 2020-04-30 | APK File | APK File | Installed successfully But I'm not able to login this app...It shows Uname and pwd incorrect.. |  | Closed
14 | 2020-05-05 | Mobile App Login | Login Page | Login Mobile App DMS |  | Closed
15 | 2020-05-05 | Customer Creation |  | DMS-Customer Creation |  | Closed
16 | 2020-05-06 | Mobile App Login | Login Page | Login Mobile App DMS |  | New
17 | 2020-05-06 | Customer Creation |  | DMS-Customer Creation |  | New
18 | 2020-05-06 | Mobile App Uname,Pwd | Login Page | Uname and Pwd |  | New
19 | 2020-05-06 | Mobile App | retailer Page | retailer details displayed in the admin approval page |  | New
20 | 2020-05-06 | Mobile App | collected amount | collected amount is displayed in the collection report page. |  | New
21 | 2020-05-06 | Automation | Popup Window | Automation does not created with in the popup window-Blocker |  | New